| Phase -1 modules and development timeline |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Modules | Features | api,/architecture (In Days) | Mobile App (In Days) | Web App (In Days) | Details |
| System Design |  | 7 |  |  | Requirement freeze, workflow diagrams, API/integration study, UI/UX wireframes |
| Architecture & Setup |  | 5 |  |  | Tech stack setup (FastAPI/Node.js backend, PostgreSQL DB, Flutter for mobile), CI/CD pipelines, staging environment |
| Database Design |  | 5 |  |  |  |
| Citizen Front-end |  |  |  |  |  |
|  | Home Screen UI | 2 | 3 | 2 | Header, footer, other components |
|  | User registration | 1 | 3 | 2 | Basic user information and mobile number verification |
|  | User login |  |  |  | OTP verification |
|  | User profile, update |  |  |  | Details of user and locality |
|  | View MP, MLA, Mayor, Councillor entities details | 3 | 3 | 3 | photo, party, symbol, contacts, constituency map, tenure |
|  | Direct message to MP, MLA, Mayor, Councillor | 1 | 2 | 2 |  |
|  | Follow MP, MLA, Mayor, Councillor profile | 1 | 1 | 1 |  |
|  | Report issues | 4 | 1 | 1 | AI geo-tagging & constituency mapping |
|  | Comment |  | 0.5 | 0.5 | User can comment on issues |
|  | Vote in polls |  | 1 | 1 | User can vote on current poll |
|  | Join groups | 2 | 4 | 3 | User can join group, view profiles, comment |
| MP, MLA, Mayor, Councillor |  |  |  |  |  |
|  | User login | 0 | 0 | 0 |  |
|  | User profile, update | 1 | 0.5 | 0.5 |  |
|  | Issues dashboard | 1 | 2 | 1 | dashboard to show open, in-progress, resolved issues |
|  | View, comment on issues | 1 | 1 | 1 |  |
| Admin control panel |  |  |  |  |  |
|  | Manage MP/MLA profile | 2 | 0 | 2 | all these modules will have add/edit/delete/activate/deactivate features |
|  | Manage user profile and roles | 1 | 0 | 2 |  |
|  | Receive/update issues | 1 | 0 | 2 |  |
|  | Broadcast updates | 3 | 0 | 3 |  |
|  | Manage reports | 3 | 0 | 4 |  |
|  | Manage configuration | 4 | 0 | 3 |  |
|  | Poll management | 5 | 0 | 5 |  |
|  | Development Days | 53 | 22 | 39 |  |
|  | Testing/QA | 7 | 7 | 7 |  |
|  | Deployment | 2 | 2 | 2 |  |
|  | Total Days | 62 | 31 | 48 |  |