# Requirement:

- Create a user-friendly and interactive website.

- Coding will be done in PHP and database in MySQL

- Website will include booking platform and payment gateway.

- A channel manager will be created for administrator so that all the bookings and booking related activities can be monitored and updated.

- Booking will be done through private platforms also like MakeMyTrip etc.

## Tech Stack

- Backend: FastAPI (Python)

- Database: PostgreSQL

- Architecture: Microservices (Docker-based deployment)

- Frontend: React.js (optional, for web interface)

- Authentication: OAuth2 / JWT

- Payment Gateway: Razorpay / Stripe

- 3rd Party Integration: MakeMyTrip APIs

- Communication: gRPC / REST between services

- Queue: RabbitMQ / Kafka (for async jobs like syncing bookings)

- Monitoring: Prometheus + Grafana

- Deployment: Kubernetes (preferred) or Docker Compose

## Core Microservices

| Service Name | Responsibility |
| --- | --- |
| User Service | Registration, login, role management (admin, customer, host) |
| Property Service | Property listing, updates, availability, images |
| Booking Service | Booking logic, availability checking, cancel/reschedule |
| Payment Service | Payment gateway integration, transaction status |
| Channel Manager Service | Sync external bookings, update availability |
| Notification Service | Email/SMS/push alerts for bookings, updates |
| Integration Service | APIs for MakeMyTrip etc. |
| Admin Dashboard Service | Central interface for monitoring all services |

## Development Phases

### Phase 1: Planning & Setup

- Define ERD (Entity Relationship Diagram) for PostgreSQL

- Set up FastAPI project skeletons for each service

- Containerize each service using Docker

- Setup centralized logging and monitoring

### Phase 2: Core Features

#### 1. User Service

- JWT-based Auth (OAuth2)

- Role-based access

- Basic profile management

#### 2. Property Service

- Host can add/edit/delete properties

- Fields: title, description, images, location, availability calendar

#### 3. Booking Service

- Book property for date range

- Cancel/reschedule booking

- Prevent double booking using row-level locking or transactions

#### 4. Payment Service

- Integrate Razorpay/Stripe

- Store transaction details

- Verify payment webhook

### Phase 3: Channel Manager & Integration

#### 5. Channel Manager Service

- Monitor all bookings

- Override, modify, or cancel any booking

- View booking statistics & sync status

#### 6. Integration Service

- APIs for MakeMyTrip

- Use OAuth or API Keys for external platforms

- Pull/push bookings and availability every X minutes via cron/async task

### Phase 4: Notification & Admin Panel

#### 7. Notification Service

- Templates for email/SMS

- Notify users/hosts on booking events

#### 8. Admin Dashboard Service

- React frontend (optional)

- View bookings, payments, errors

- Manage users, properties, integrations

### Phase 5: Testing & Deployment

- Unit tests for all services

- Integration tests for end-to-end flow

- Setup staging and production environments (e.g., Kubernetes)

- CI/CD pipeline using GitHub Actions

Estimate & timeline

| Module | 1 Man Days | Description |
| --- | --- | --- |
| Project Setup & Architecture | 4 | Setup Git, Docker, CI/CD, database, service skeletons |
| Landing page design | 2 | Three revision in landing page UI |
| Static pages’ content | 2 |  |
| User Authentication | 3 | Signup/login, JWT, roles (admin, host, customer) |
| Property Management | 4 | CRUD for properties, availability calendar |
| Booking Engine | 7 | Booking flow, cancellation, calendar conflict checks |
| Payment Gateway Integration | 4 | Razorpay/Stripe, webhook handling, test sandbox |
| Channel Manager | 4 | Admin view of all bookings, status update, sync status |
| External Integrations | 7 | MakeMyTrip API integration, scheduler, sync logic |
| Notification System | 4 | Email/SMS alerts on booking, payment, cancellation |
| Admin Dashboard (Backend APIs) | 7 | APIs for admin to monitor users/bookings/payments |
| Testing (Unit & E2E) | 5 | Pytest + test coverage for all services |
| Deployment & Monitoring | 3 | Docker/Kubernetes setup, logs, Prometheus + Grafana |
| Documentation | 1 | README, API docs (Swagger/OpenAPI), setup guides |
| Total | 57 | Days |
| Total Cost | 2,28,000 | INR |
| Resources Required | 2 | Front-end: 1, Back-end: 1 |